## Sheet1
FIELD PROGRESS REPORT
1. Overview
| Project Name: | New Hope |  |  | Implementing Partner:
| Project Lead Member: | Sue Black |  |  | Project Location: | Ethiopia
| Currency used in Country of Implementation: | Ethiopian Birr |  |  | Reporting Period: | July 1 to Dec 31 2019
2. Opening Balance & Financial Summary | [6 empty] | Line Ref
[5 empty] | Last Report Date | local currency amount
| Last Report Ending Balance |  |  |  | Jan – June 2019 | 350399.57 | A
3. Income (Transfers) this reporting period
This is a list of transfers that happened in the last reporting period. Please fill in local currencies,these are available on your proof of transfers. (You can see these on your dashboard)
Listing of transfers made overseas:
| Notes, if any |  |  | Date | CAD$ transferred | Local Curr received
| transfer |  |  | 30/10/2019 | 6240 | 137371.55
|  |  |  | Total transferred | 6240 | 137371.55 | B
Other Income and Microloans |  |  | Notes/Description |  |  | Amount(local Curr)
| Other Income | [5 empty] | C
| Loans Paid back during this period |  |  |  |  | 80500 | D
E
|  |  | Total Other Income and MicroLoans (C+D+E) |  |  | 80500 | F
|  |  | New Micro Loans Given during this period |  |  | 60500 | G
|  |  | Total Funds Available (A+B+FminusG) |  |  | 507771.12 | H
4. Expense Budget vs. Actual In The Field
Here is where you fill in the items you put on your annual plan, we want to see how close or far away you got with your annual plan! Please also include any outside funding that occurred for the specific items in your plan. This lets us make sure there is no double funding. If you go into a deficit or a perfect zero with the your ending balance, you will be asked for more information and need to possibly redo your report, please don't round up or down your numbers, we want exact numbers for accounting.
| Current Exchange Rate to Cdn$: | 22
| Item |  |  |  | Annual Budget (Local) | Actual Cost local currency (Current Period)
| The amount on line 33 is for both 33 &34 *VSLA 10 Groups training and related expenses |  |  |  | 326000 | 62572.54
|  |  | *VSLA 10 Groups seed money expenses |  |  | 100000
| Admin related expenses 25,300 + 4539.50 (proj officer exp.) |  |  |  | 94000 | 29839.5
|  |  | Project Director salary for 6 months (a raise was necessary) |  | 34800 | 32425
|  |  | Project Accountant salary for 6 mths (a raise was necessary) |  | 20400 | 38910
| Special Needs Expenses |  |  |  | 30000 | 18710
| Books/Education expenses |  |  |  | 10800 | 6284
| New Hope new office rent share |  |  |  | 24000 | 13500
|  |  | Total Expense |  | 540000 | 302241.04 | I
| Ending Balance(H minus I) This is to be reported as beginning balance for next reporting period |  |  |  |  | 205530.08 | J
4. Activities Plan vs. Actual In The Field – During This Reporting Period
Please list activities that happenedin the field (not in Canada). We want to know what you were able to accomplish with donor support. (Obstacles are in the next section so use this space to go over your successes!)
| Activities/Objectives - (PLAN) |  |  | Activities/ Objectives - (Actual)
| Form, train & fund new VSLA groups; f/up VSLA's till independence |  |  | Same as planned. We now have 30 VSLA groups!
| Provide indiv. MicroLoans to start small bus. to those unsuited for VSLA |  |  | Continued providing individual microloans to those unsuited for VSLA
| Provide emerg. assist. such as medicine, food etc. to people in our comm. |  |  | Provided emergency assistance as planned.
6. Lessons Learned this reporting period, in the field
please list only challenges that happenedin the field – not in Canada. What obstacles did the project face that you did overcome
or still need to overcome, what is your goal to overcome it?
What Challenges did you face?
VSLA training said to give each VSLA member seed money of approximately 1,500 birr each ( approx. $75). Each group has 20 members so this is a lot of money which is difficult to raise and we are concerned about it not being sustainable. We had been giving about 1,000 birr each. We considered asking members to pay it back, as a loan, but then we would be back into high admin. plus this would be hard for such poor people.
What Helped you overcome challenges or succeed in meeting your objectives?
We decided to try giving 500 birr per person as seed money instead of $1,000. This will allow us to be able to start twice as many groups with the same amount of money and still gets people started and avoids the additional admin and legal issues of collecting loans.
7. Stories & Photos in the field, this reporting period
Please include a story or incident of a beneficiary, staff or person associated with this project that reflects how the funds donated to this project have helped. Please attach photos.
Please write and send stories as separate documents using Word format and send pictures as .jpg photos.